## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload documents for processing | MUST HAVE | File handling module | Akshaya B | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a system, I want to process documents into embeddings | MUST HAVE | LangChain, Embedding model | Akshaya B | 3- Completed
Sprint 3 | Sprint 3 | US-03 | As a user, I want to ask questions based on documents | MUST HAVE | Vector DB, Retriever | Akshaya B | 3- Completed
Sprint 3 | Sprint 3 | US-04 | As a system, I want to retrieve relevant document chunks | MUST HAVE | ChromaDB | Akshaya B | 3- Completed
Sprint 4 | Sprint 4 | US-05 | As a user, I want conversational memory for follow-up queries | SHOULD HAVE | Chat history management | Akshaya B | 3- Completed
Sprint 3 | Sprint 3 | US - 06 | As a user, I want to view chat history | SHOULD HAVE | State management | Akshaya B | 3- Completed
Sprint 4 | Sprint 3 | US -07 | As a system, I want real-time UI updates | SHOULD HAVE | Reflex state | Akshaya B | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 19 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Implement file upload functionality | 2026-01-02 | 2026-10-02 | Akshaya B | Build | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Document preprocessing & chunking | 25-02-2026 | 28-02-2026 | Akshaya B | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Implement embedding generation | 2026-03-03 | 2026-03-06 | Akshaya B | Integration Test | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T04 | Setup vector database (ChromaDB) | 2026-03-10 | 2026-03-17 | Akshaya B | System Test | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Issues in uploading and reading multiple document formats | Fixed file handling and added format validation
Sprint 1 | Day 3 | Errors in document loading using loader | Corrected file paths and loader configuration
Sprint 2 | Day 4 | Irrelevant document chunks retrieved | Improved chunking and retrieval logic
Sprint 2 | Day 5 | Embedding generation taking longer time | Optimized processing and reduced chunk size
Sprint 2 | Day 6 | Vectorstore not updating with new documents | Implemented dynamic add_documents logic
Sprint 3 | Day 6 | Chat history not used in follow-up queries | Implemented history injection in prompt
Sprint 3 | Day 7 | UI not updating after new responses | Fixed state update using new object assignment
Sprint 3 | Day 8 | Inconsistent answers due to poor query clarity | Added corrective RAG with query rewriting

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-02 | 2026-07-02 | Akshaya B | Structured file handling | Ignoring file validation | Following coding standards | Added file format validation
2 | Sprint 1 | 2026-01-02 | 2026-07-02 | Akshaya B | Proper document preprocessing | Hardcoded paths | Testing modules regularly | Improved loader configuration
3 | Sprint 2 | 2026-08-02 | 14-02-2026 | Akshaya B | Optimizing chunking strategy | Using large chunk sizes | Improving retrieval logic | Adjusted chunk size and overlap
4 | Sprint 2 | 2026-08-02 | 14-02-2026 | Akshaya B | Enhancing embedding efficiency | Reprocessing entire dataset | Using vector database effectively | Implemented incremental document addition
5 | Sprint 3 | 15-03-2026 | 21-03-2026 | Akshaya B | Using conversation history in prompts | Ignoring past interactions | Improving chatbot responses | Added history injection mechanism
6 | Sprint 3 | 15-03-2026 | 21-03-2026 | Akshaya B | Implementing corrective RAG | Accepting irrelevant responses | Refining prompt engineering | Added relevance check and query rewriting
7 | Sprint 3 | 15-03-2026 | 21-03-2026 | Akshaya B | Improving UI responsiveness | Direct state mutation | Using reactive state updates | Fixed UI updates using new object assignment
8 | Sprint 3 | 15-03-2026 | 21-03-2026 | Akshaya B | Enhancing testing and debugging | Skipping edge case testing | Continuous testing | Added test cases and fixed identified bugs